## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Blue
Project: Solar tracker
University of Michigan
Zhuoyuan Liu
Project start date: | 2024-07-25 | [10 empty] | Scrolling increment: | [5 empty] | 44
Milestone marker: | 1 | 1 |  |  | September | [27 empty] | October
 | time axis 2024-09-07 to 2024-11-01
Milestone description | Objective | Progress | Start | Days | time axis 2024-09-07 to 2024-11-01
Simulation
Task 1: Matlab rigid body sim |  | 100% | 2024-07-25 | 3
Task 2: Add string mechanics (yaw change) | The string will tighten/relax, causing yaw movement of the panel | 80% | 2024-08-01 | 20
Task 3: Add angle reading | Read the azimuth/elevation angles of the panel; also read the hour angle/declination angles; also read the Euler angles for backup | 70% | 2024-08-09 | 30
Task 4: Simulate sun motion | Simulate the sun's motion in the celestial sphere in any specific day of the year | 100% | 2024-08-12 | 30
Task 5: Check tracking efficiency | Use the difference of the norm vector and the sun's vector as the error, and make statistical analysis | 50% | 2024-08-16 | 30
Task 6: Trade study on multi-axis mechanism | Since the sun at the horizon can be to the north or to the south, but the panel can only face the south, might need to add another rotation to compensate | 30% | 2024-09-19 | 14
Components selection
Task 1: String actuator | Maybe motors, maybe hydraulic/pneumatic system | 50% | 2024-10-08 | 30
Task 2: Strings | Durable, proper friction… | 0% | 2024-10-09 | 30
Task 3: Angle sensors | Either use the encoder of the motors, or place a 9-axis IMU on the panel | 0% | 2024-11-15 | 30
Task 4: Miscellaneous | Wires, bolts, screws, etc. | 10% | 2024-10-21 | 30
Mechanical design
Task 1: Actuator holder | The 'cross' structure holding the actuators (motors) | 0% | 2024-10-17 | 40
Task 2: Solar panel holder | Design a frame that can hold the panel, and can be controlled by the strings | 0% | 2024-10-17 | 30
Task 3: Shell | Opaque and transparent shells | 0% | 2024-10-31 | 10
Task 4: String holder | The 'cross' structure with holes for the string to go through and the winches on the motors. The winches must be highly fricative. | 0% | 2024-10-17 | 30
Task 5: Electrical bay | A container mounted on top of the string holder that stores the motors, the embedded board etc. | 0% | 2024-11-05 | 30
Electrical design
Task 1: Power distribution circuit board | A PCB that distributes power generated from the panels to: Actuators, microcontroller, etc. | 0% | 2024-11-20 | 30
Task 2: Signal pins extension circuit board | Extend the pins of the MCU to the motors, the encoders, etc. | 0% | 2024-11-20 | 30
Task 3
Task 4
Embedded system
Task 1: Mircro Control Unit | Select a COTS development board for experiments, and later change to self-designed control unit using chip | 0% | 2024-10-26 | 15
Task 2: Motor driver | Write the driver program that allows the MCU to control the motors | 0% | 2024-11-15 | 30
Task 3: Tracking Algorithm | One motor should follow the hour angle of the sun during each day (theoretically this is a constant-speed rotation about a fixed axis (polar axis)), while the other motor will slightly rotate to follow the declination of the sun only in each day's morning. | 0% | 2024-10-16 | 90
Task 4: Control system | Design an open-loop (or closed-loop) angles following algorithm based on motor-panel angle relation | 0% | 2024-11-08 | 90
System integration | bar: 2024-09-20 to 2024-10-19
Task 1: Components | Order COTS components, or 3D print/order designed components | 0% | 2025-01-01 | 30 | bar: 2024-09-20 to 2024-09-29
Task 2: Assembly | Assemble the prototype | 0% | 2025-02-01 | 10 | bar: 2024-09-20 to 2024-10-19
Task 3: Testing | Real test and troubleshooting/improving | 0% | 2025-02-11 | 30
To add more data, Insert new rows ABOVE this one